## Issue Effort Report
Milestone | Issue # | Summary of tasks | Estimate (mins) | Coding Effort (mins) | Non-Coding Effort (mins) | Estimator | Implementors | Status | URL | Notes
M1 | 3 | Add corkboard background |  |  |  | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/3 | Estimator assumed from assignee; verify.
M1 | 17 | Add interest selection section |  |  |  | AnnieP211 | AnnieP211 | Done | https://github.com/bowlletins/Bowlletins/issues/17 | Estimator assumed from assignee; verify.
M1 | 5 | Create sticky note component |  |  |  | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/5 | Estimator assumed from assignee; verify.
M1 | 16 | Implement profile photo upload |  |  |  | AnnieP211 | AnnieP211 | Done | https://github.com/bowlletins/Bowlletins/issues/16 | Estimator assumed from assignee; verify.
M1 | 15 | Add profile input fields |  |  |  | AnnieP211 | AnnieP211 | Done | https://github.com/bowlletins/Bowlletins/issues/15 | Estimator assumed from assignee; verify.
M1 | 18 | Style profile page |  |  |  | AnnieP211 | AnnieP211 | Done | https://github.com/bowlletins/Bowlletins/issues/18 | Estimator assumed from assignee; verify.
M1 | 14 | Setup profile page layout |  |  |  | AnnieP211 | AnnieP211 | Done | https://github.com/bowlletins/Bowlletins/issues/14 | Estimator assumed from assignee; verify.
M1 | 6 | Add sticky notes to landing page |  |  |  | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/6 | Estimator assumed from assignee; verify.
M1 | 7 | Style landing page |  |  |  | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/7 | Estimator assumed from assignee; verify.
M1 | 23 | Style flyer detail page |  |  |  | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/23 | Estimator assumed from assignee; verify.
M1 | 8 | Setup dashboard layout |  |  |  | terisa-lau | terisa-lau | Done | https://github.com/bowlletins/Bowlletins/issues/8 | Estimator assumed from assignee; verify.
M1 | 9 | Add sidebar navigation |  |  |  | terisa-lau | terisa-lau | Done | https://github.com/bowlletins/Bowlletins/issues/9 | Estimator assumed from assignee; verify.
M1 | 26 | Polish Homepage |  |  |  | CadenTran44 | CadenTran44 | Done | https://github.com/bowlletins/Bowlletins/issues/26 | Estimator assumed from assignee; verify.
M1 | 24 | Setup Vercel deployment |  |  |  | CadenTran44 | CadenTran44 | Done | https://github.com/bowlletins/Bowlletins/issues/24 | Estimator assumed from assignee; verify.
M1 | 27 | Polish Footer UI |  |  |  | CadenTran44 | CadenTran44 | Done | https://github.com/bowlletins/Bowlletins/issues/27 | Estimator assumed from assignee; verify.
M1 | 2 | Setup landing page hero layout |  |  |  | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/2 | Estimator assumed from assignee; verify.
M1 | 22 | Add action buttons |  |  |  | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/22 | Estimator assumed from assignee; verify.
M1 | 32 | redirecting sign up to profile |  |  |  | AnnieP211 | AnnieP211 | Done | https://github.com/bowlletins/Bowlletins/issues/32 | Estimator assumed from assignee; verify.
M1 | 34 | New sign in page |  |  |  | AnnieP211 | AnnieP211 | Done | https://github.com/bowlletins/Bowlletins/issues/34 | Estimator assumed from assignee; verify.
M1 | 33 | fixing landing page login card |  |  |  | AnnieP211 | AnnieP211 | Done | https://github.com/bowlletins/Bowlletins/issues/33 | Estimator assumed from assignee; verify.
M1 | 19 | Setup flyer detail layout |  |  |  | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/19 | Estimator assumed from assignee; verify.
M1 | 20 | Display flyer information |  |  |  | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/20 | Estimator assumed from assignee; verify.
M1 | 21 | Add contact section |  |  |  | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/21 | Estimator assumed from assignee; verify.
M1 | 28 | Fix Categories tab |  |  |  | CadenTran44 | CadenTran44 | Done | https://github.com/bowlletins/Bowlletins/issues/28 | Estimator assumed from assignee; verify.
M1 | 43 | Navbar Cleanup |  |  |  | CadenTran44 | CadenTran44 | Done | https://github.com/bowlletins/Bowlletins/issues/43 | Estimator assumed from assignee; verify.
M1 | 36 | Link profile settings update to profile dashboard |  |  |  | terisa-lau | terisa-lau | Done | https://github.com/bowlletins/Bowlletins/issues/36 | Estimator assumed from assignee; verify.
M2 | 35 | fix navbar minimization issue | 8 | 6 | 1 | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/35 | Estimator assumed from assignee; verify.
M2 | 38 | Make About page | 60 | 42 | 9 | CadenTran44 | CadenTran44 | Done | https://github.com/bowlletins/Bowlletins/issues/38 | Estimator assumed from assignee; verify.
M2 | 106 | Categories link under Explore dropdown does not work | 60 | 43 | 28 | AnnieP211 | AnnieP211 | Done | https://github.com/bowlletins/Bowlletins/issues/106 | Estimator assumed from assignee; verify.
M2 | 39 | Redirect About page | 5 | 2 | 0 | CadenTran44 | CadenTran44 | Done | https://github.com/bowlletins/Bowlletins/issues/39 | Estimator assumed from assignee; verify.
M2 | 89 | Redirect after submission | 5 | 2 | 0 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/89 | Estimator assumed from assignee; verify.
M2 | 90 | Protect create flyer page | 10 | 11 | 3 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/90 | Estimator assumed from assignee; verify.
M2 | 105 | Fix page content overlapping footer on small screens | 40 | 24 | 20 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/105 | Estimator assumed from assignee; verify.
M2 | 86 | Add category dropdown to form | 5 | 2 | 1 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/86 | Estimator assumed from assignee; verify.
M2 | 87 | Connect form to database | 12 | 9 | 2 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/87 | Estimator assumed from assignee; verify.
M2 | 88 | Add form validation | 7 | 9 | 1 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/88 | Estimator assumed from assignee; verify.
M2 | 40 | Style About page | 60 | 69 | 0 | CadenTran44 | CadenTran44 | Done | https://github.com/bowlletins/Bowlletins/issues/40 | Estimator assumed from assignee; verify.
M2 | 42 | Set up vercel database | 1 | 1 | 0 | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/42 | Estimator assumed from assignee; verify.
M2 | 84 | Setup create flyer page layout | 15 | 14 | 3 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/84 | Estimator assumed from assignee; verify.
M2 | 52 | Add search bar to navbar | 2 | 2 | 0 | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/52 | Estimator assumed from assignee; verify.
M2 | 54 | Create browser/ explore page | 46 | 22 | 20 | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/54 | Estimator assumed from assignee; verify.
M2 | 11 | Implement saved posts section | 90 | 23 | 61 | terisa-lau | terisa-lau | Done | https://github.com/bowlletins/Bowlletins/issues/11 | Estimator assumed from assignee; verify.
M2 | 53 | Update landing page layout | 6 | 2 | 4 | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/53 | Estimator assumed from assignee; verify.
M2 | 55 | Make Contact Us page | 60 | 32 | 14 | CadenTran44 | CadenTran44 | Done | https://github.com/bowlletins/Bowlletins/issues/55 | Estimator assumed from assignee; verify.
M2 | 56 | Redirect Contact Us page | 5 | 2 | 0 | CadenTran44 | CadenTran44 | Done | https://github.com/bowlletins/Bowlletins/issues/56 | Estimator assumed from assignee; verify.
M2 | 57 | Style Contact Us page | 60 | 49 |  | CadenTran44 | CadenTran44 | Done | https://github.com/bowlletins/Bowlletins/issues/57 | Estimator assumed from assignee; verify.
M2 | 58 | Link main sign in page to database | 30 | 5 | 17 | terisa-lau | terisa-lau | Done | https://github.com/bowlletins/Bowlletins/issues/58 | Estimator assumed from assignee; verify.
M2 | 49 | Add empty state for categories | 20 | 17 | 5 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/49 | Estimator assumed from assignee; verify.
M2 | 47 | Create FlyerCard component | 45 | 37 | 10 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/47 | Estimator assumed from assignee; verify.
M2 | 69 | Add category enum to Prisma schema | 5 | 3 | 1 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/69 | Estimator assumed from assignee; verify.
M2 | 50 | Link navbar categories to pages | 5 | 3 | 1 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/50 | Estimator assumed from assignee; verify.
M2 | 48 | Display flyer cards on category page | 5 | 9 | 1 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/48 | Estimator assumed from assignee; verify.
M2 | 46 | Fetch flyers by category from database | 10 | 4 | 5 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/46 | Estimator assumed from assignee; verify.
M2 | 61 | Make profile button viewable only when signed in | 20 | 3 | 13 | terisa-lau | terisa-lau | Done | https://github.com/bowlletins/Bowlletins/issues/61 | Estimator assumed from assignee; verify.
M2 | 51 | Add flyer count per category | 8 | 3 | 2 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/51 | Estimator assumed from assignee; verify.
M2 | 63 | Fix Sign Up page | 15 | 8 | 18 | terisa-lau | terisa-lau | Done | https://github.com/bowlletins/Bowlletins/issues/63 | Estimator assumed from assignee; verify.
M2 | 73 | Add explore/browse to navbar | 1 |  |  | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/73 | Estimator assumed from assignee; verify.
M2 | 76 | Fix Navbar Size | 10 | 7 |  | CadenTran44 | CadenTran44 | Done | https://github.com/bowlletins/Bowlletins/issues/76 | Estimator assumed from assignee; verify.
M2 | 78 | Flyer Database Schema Update | 25 | 13 | 29 | terisa-lau | terisa-lau | Done | https://github.com/bowlletins/Bowlletins/issues/78 | Estimator assumed from assignee; verify.
M2 | 80 | Make jobs and flyer posted look nicer | 10 | 11 | 3 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/80 | Estimator assumed from assignee; verify.
M2 | 45 | Setup categories page layout | 25 | 20 | 7 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/45 | Estimator assumed from assignee; verify.
M2 | 82 | Navbar minimization update | 1 | 0 | 1 | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/82 | Estimator assumed from assignee; verify.
M2 | 85 | Add create flyer form fields | 20 | 14 | 4 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/85 | Estimator assumed from assignee; verify.
M2 | 92 | Create Flyer Adding to Database | 50 | 7 | 42 | terisa-lau | terisa-lau | Done | https://github.com/bowlletins/Bowlletins/issues/92 | Estimator assumed from assignee; verify.
M2 | 97 | Make Save Button on Flyers Usable | 20 | 12 | 23 | terisa-lau | terisa-lau | Done | https://github.com/bowlletins/Bowlletins/issues/97 | Estimator assumed from assignee; verify.
M2 | 107 | Categories link under Explore dropdown does not work | 20 | 10 | 3 |  |  | Done | https://github.com/bowlletins/Bowlletins/issues/107 | Missing assignee/estimator.
M2 | 102 | Add db to explore page | 1 | 1 | 0 | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/102 | Estimator assumed from assignee; verify.
M2 | 109 | Polish Contact Page | 10 | 11 |  | CadenTran44 | CadenTran44 | Done | https://github.com/bowlletins/Bowlletins/issues/109 | Estimator assumed from assignee; verify.
M2 | 124 | Add M2 explore database and Playwright tests |  |  |  | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/124 | Estimator assumed from assignee; verify.
M3 | 172 | Make admin message page |  |  |  | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/172 | Estimator assumed from assignee; verify.
M3 | 127 | MyFlyers Page | 30 | 8 | 12 | terisa-lau | terisa-lau | Done | https://github.com/bowlletins/Bowlletins/issues/127 | Estimator assumed from assignee; verify.
M3 | 4 | Implement search bar | 200 | 138 | 154 | AnnieP211 | AnnieP211 | Done | https://github.com/bowlletins/Bowlletins/issues/4 | Estimator assumed from assignee; verify.
M3 | 25 | Fix navigation routing | 5 | 4 | 0 | CadenTran44 | CadenTran44 | Done | https://github.com/bowlletins/Bowlletins/issues/25 | Estimator assumed from assignee; verify.
M3 | 59 | Polish Sign In page | 3 | 2 | 0 | CadenTran44 | CadenTran44 | Done | https://github.com/bowlletins/Bowlletins/issues/59 | Estimator assumed from assignee; verify.
M3 | 67 | Sign up Errors | 10 | 2 | 5 | terisa-lau | terisa-lau | Done | https://github.com/bowlletins/Bowlletins/issues/67 | Estimator assumed from assignee; verify.
M3 | 140 | Filter private flyers from public views | 5 | 2 | 1 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/140 | Estimator assumed from assignee; verify.
M3 | 75 | Remove sign in from landing page (When user has signed in) | 2 | 1 | 0 | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/75 | Estimator assumed from assignee; verify.
M3 | 79 | Update Profile for Admin view/access | 45 | 23 | 29 | terisa-lau | terisa-lau | Done | https://github.com/bowlletins/Bowlletins/issues/79 | Estimator assumed from assignee; verify.
M3 | 144 | Make admin annocment tab | 40 | 52 | 14 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/144 | Estimator assumed from assignee; verify.
M3 | 137 | Add isPrivate and expiresAt fields to Flyer model | 2 | 1 | 0 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/137 | Estimator assumed from assignee; verify.
M3 | 138 | Add private toggle to Create Flyer form | 20 | 16 | 5 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/138 | Estimator assumed from assignee; verify.
M3 | 139 | Add private toggle on flyer detail page for owner | 20 | 12 | 3 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/139 | Estimator assumed from assignee; verify.
M3 | 141 | Auto-private flyers after 24 hours | 10 | 4 | 12 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/141 | Estimator assumed from assignee; verify.
M3 | 100 | Fix redirection from categories to explore | 2 | 1 | 1 | CadenTran44 | CadenTran44 | Done | https://github.com/bowlletins/Bowlletins/issues/100 | Estimator assumed from assignee; verify.
M3 | 101 | Fix sign in redirect after signing in | 2 | 1 | 1 | AnnieP211 | AnnieP211 | Done | https://github.com/bowlletins/Bowlletins/issues/101 | Estimator assumed from assignee; verify.
M3 | 103 | Polish Category pages | 30 | 37 | 4 | CadenTran44 | CadenTran44 | Done | https://github.com/bowlletins/Bowlletins/issues/103 | Estimator assumed from assignee; verify.
M3 | 104 | Add a back button when viewing flyer details | 2 | 1 | 1 | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/104 | Estimator assumed from assignee; verify.
M3 | 110 | redirect "explore what's happening" button to explore page | 2 | 1 | 1 | AnnieP211 | AnnieP211 | Done | https://github.com/bowlletins/Bowlletins/issues/110 | Estimator assumed from assignee; verify.
M3 | 111 | indicate info. is mandatory for create flyer page | 20 | 7 | 6 | AnnieP211 | AnnieP211 | Done | https://github.com/bowlletins/Bowlletins/issues/111 | Estimator assumed from assignee; verify.
M3 | 112 | fix single column form layout for create a flyer | 15 | 5 | 6 | AnnieP211 | AnnieP211 | Done | https://github.com/bowlletins/Bowlletins/issues/112 | Estimator assumed from assignee; verify.
M3 | 113 | decide whether you'd like to keep 2 links that lead to homepage | 1 | 1 | 0 | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/113 | Estimator assumed from assignee; verify.
M3 | 114 | create a place where users can see flyers that has been auto-deleted | 2 | 2 | 2 | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/114 | Estimator assumed from assignee; verify.
M3 | 115 | users guide & developers guide | 1 | 0 | 1 | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/115 | Estimator assumed from assignee; verify.
M3 | 142 | Show private status indicator on flyer cards and detail page | 15 | 8 | 10 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/142 | Estimator assumed from assignee; verify.
M3 | 146 | Auto-private flyers after event date passes | 15 | 5 | 4 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/146 | Estimator assumed from assignee; verify.
M3 | 116 | implement like button/numbers inc. | 130 | 54 | 72 | AnnieP211 | AnnieP211 | Done | https://github.com/bowlletins/Bowlletins/issues/116 | Estimator assumed from assignee; verify.
M3 | 119 | Create update flyer page | 2 | 4 | 1 | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/119 | Estimator assumed from assignee; verify.
M3 | 120 | Implement RSVP | 20 | 7 | 14 | terisa-lau | terisa-lau | Done | https://github.com/bowlletins/Bowlletins/issues/120 | Estimator assumed from assignee; verify.
M3 | 129 | Allow admin to edit/delete users/flyers in the admin console | 2 |  |  | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/129 | Estimator assumed from assignee; verify.
M3 | 130 | Style Sign Out Page | 25 | 22 | 6 | CadenTran44 | CadenTran44 | Done | https://github.com/bowlletins/Bowlletins/issues/130 | Estimator assumed from assignee; verify.
M3 | 133 | Update settings to include change password | 1 | 2 | 0 | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/133 | Estimator assumed from assignee; verify.
M3 | 134 | Add "create username" | 5 | 5 | 0 | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/134 | Estimator assumed from assignee; verify.
M3 | 135 | Sync update picture to profile circle |  |  |  | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/135 | Estimator assumed from assignee; verify.
M3 | 136 | Update password requirements | 2 | 2 | 0 | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/136 | Estimator assumed from assignee; verify.
M3 | 143 | Add picture to profile icon | 15 | 16 | 0 | CadenTran44 | CadenTran44 | Done | https://github.com/bowlletins/Bowlletins/issues/143 | Estimator assumed from assignee; verify.
M3 | 147 | Style Change Password Page | 25 | 31 | 0 | CadenTran44 | CadenTran44 | Done | https://github.com/bowlletins/Bowlletins/issues/147 | Estimator assumed from assignee; verify.
M3 | 153 | Fix not being able to create flyer when creating it public | 20 | 6 | 20 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/153 | Estimator assumed from assignee; verify.
M3 | 151 | Style Admin Page | 7 | 4 | 5 | terisa-lau | terisa-lau | Done | https://github.com/bowlletins/Bowlletins/issues/151 | Estimator assumed from assignee; verify.
M3 | 156 | turn home into post button for signed in users | 1 | 1 | 0 | Tamelab | Tamelab | Done | https://github.com/bowlletins/Bowlletins/issues/156 | Estimator assumed from assignee; verify.
M3 | 160 | Allow Creator to edit flyer | 60 | 93 | 8 | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/160 | Estimator assumed from assignee; verify.
M3 | 165 | Explore Page Polish | 5 | 6 | 1 | CadenTran44 | CadenTran44 | Done | https://github.com/bowlletins/Bowlletins/issues/165 | Estimator assumed from assignee; verify.
M3 | 172 | Make admin message page |  |  |  | ThomasTran808 | ThomasTran808 | Done | https://github.com/bowlletins/Bowlletins/issues/172 | Estimator assumed from assignee; verify.

## Team Member Experience
Team Member | Software Development Experience (months) | How was coding effort tracked | How was non-coding effort tracked?
Tamela Brinson | 12 | Time actively typing and debugging code in VSCode; GitHub issue/commit updates; AI coding help counted when used for code. | Manual notes for planning, documentation, researching errors, AI brainstorming, testing, and project board updates.
Annie Pham | 6 | Time spent typing code. | Time asking AI to help brainstorm, point out possible problems, and suggest ways to improve current written code.
Caden Tran | 19–20 | Time typing code. | Time asking AI for help and designing prototypes for pages.
Terisa Lau | 8 | Time spent typing out code. | Time spent looking at documentation, debugging, AI generation, and testing.
Thomas Tran | 20 | Time coding. | Researching, learning different concepts, and asking AI for help.

## Summary
Bow-lletins Effort Estimation Summary
Milestone | Issue Count | Estimated Effort | Coding Effort | Non-Coding Effort | Issues Missing Data
M1 | 26 | 0 | 0 | 0 | 26
M2 | 43 | 2093 | 1272 | 706
M3 | 43 | 2058 | 1708 | 694 | 4
Team Member | Issue Count | Estimated Effort | Coding Effort | Non-Coding Effort | Total Actual Effort
AnnieP211 | 15 | 429 | 249 | 268 | 517
CadenTran44 | 21 | 380 | 333 | 35 | 368
Tamelab | 26 | 2506 | 1882 | 680 | 2562
ThomasTran808 | 34 | 454 | 391 | 146 | 537
terisa-lau | 15 | 362 | 115 | 268 | 383